## Cover Page
NHS Digital Hazard Log - Connecting Systems - Patient Flags API
Programme |  | Document Record ID Key
Sub-Prog / Project
Prog. Director |  | Status | Published
Owner |  | Version | 1
Author | Bruno Tchek | Version Date | 2024-08-19
Connecting Systems - Patient Flags API Hazard Log
We provide this hazard log template, pre-populated with the minimum hazards you must address as part of your clinical safety review, when integrating with the Patient Flags API. If you identify more than these minimum hazards, add them to your hazard log. You can use our template or create your own, so long as it includes the same hazards.

## Version History
Amendment History:
Version | Date | Amendment History
0.1 | 22.10.2020 | First draft in view to consolidate the risk assessment of the RA Flag in SCRa which is evidenced in the SPINE 2 Hazard Log 3.2 and the one carried out in support of the RA API.
0.2 | 17.11.2020 | Revised following the identification of risks associated to the RA API with respect to the API platform and the connecting systems.
0.3 | 20.07.2021 | Revised following the identification of risks inherent to the central solution, RA API.
0.4 | 29.07.2021 | Follow-up on mapping all the SA clinical impacting risks attributed to the central solution, the connecting systems and the API platform.
0.5 | 13.10.2021 | Edited in conformance to the new hazard log template.
0.6 | 30.12.2021 | Revised the hazards names and associated possible harms.
0.7 | 2023-02-03 | Revised following various updates to NCRS, Spine, and the API.
0.8 | 2024-07-19 | Initial Version - Patient Flag API - Connected Systems
1 | 2024-08-19 | Published
Reviewers:
This document must be reviewed by the following:
Name |  | Title / Responsibility | Date | Version
Zak Bickhan |  | CSG Clinical Safety Officer |  | 0.5
Raman Behl |  | Clinical Lead - Integrating Care Programmes |  | 0.5
Munish Jokhani |  | Assurance Lead for API platform |  | 0.5
Dr Rob Jeeves |  | SCR Primary Care Clinical Lead | 2023-02-03 | 0.7
Dr Rob Jeeves |  | SCR Primary Care Clinical Lead |  | 0.8
Dr Rob Jeeves |  | SCR Primary Care Clinical Lead |  | 1
Approved by:
This document must be approved by the following:
Name |  | Title / Responsibility | Date | Version
Clinical Safety Group |  | Approval Board |  | 0.5
Distribution:
NHS Digital Clinical Safety Group
Document Status:
The controlled copy of this document is maintained in the NHS Digital Electronic Document and Records Management System. Any copies of this document held outside of that system, in whatever format (e.g. paper, email attachment), are considered to have passed out of control and should be checked for currency and validity.

## Patient Flag API Hazard Log
| Hazard Assessment |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Hazard Description |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[5 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
| Effect | Hazard | Harm | Possible Causes | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
PF001 | Patient Flag API fails to return any flags when theyare available in the data store | A patient or citizen has a flag against their record but this is not visible to the halth care professional. | A Health care professional is unaware of a patient flag causing Inappropriate care and/or delay in the delivery of care. | Connecting Systems:
Connecting system sends a valid but incorrect token.
Connecting system sends an invalid token.
Incorrect data sent by connecting system i.e. structure correct, data incorrect.
The connecting system is not compliant with the latest approved API specification for a given interaction (including create, update, and delete) i.e. structure incorrect, data correct.
PF002 | Failure to return complete set of requested flags and supporting information | Some Patient Flags and/or supporting information unavailable for the Health Care Practitioner when consulting / delivering care to the patient. | Inappropriate care and/or delay in the delivery of care. | Connecting Systems:
Lack of response from the Patient Flag API to an end user request. Request times out.
Failure to identify appropriate patient to retrieve the Flag due not recognising the NHS number provided
RBAC controls or local equivalent are not implemented correctly - access to flags is not given when it should be
PF003 | Patient Flag returns incorrect or corrupted data | A patient or citizen experiences an action performed by a Health Care Professional which is based on misleading flag information. This may be the inclusion of an action or exclusion of an action which should have been performed. | Inappropriate care and/or delay in the delivery of care. A patient may also suffer from psychological/mental distress. | Connecting Systems:
A flag belonging to Patient A is incorrectly displayed in Patient B's record
Erroneous response from the API to an end user request
An incorrect identifier (NHS Number) is sent in the message by the connecting system.
Connecting system fails to correctly process response from Patient Flag API (System level).
Connecting system fails to correctly present the data returned from Patient Flag API (Presentation layer). This would be due to the connecting system being unable to interpret the response from the Patient Flags API.
Connecting system fails to trigger/complete a manual query request of the Patient Flag for an individual patient from Spine.
Connecting system does not implement the specification correctly.
PF004 | Patient Flag API Fails to upload update/delete a flag as instructed, due to system failure. | HCP is unaware of reasonable adjustments relevant to a patient. The RA Flag data may be imcomplete / out of date. Also, the HCP is not notified of the failure to upload a change to a RA Flag on Spine, so does not know that this action needs repeating. | Inappropriate care and/or delay in the delivery of care due to inaccurate information presented to the HCP | Connecting Systems:
Connecting system sends a valid but incorrect token.
Connecting system sends an invalid token.

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Severity Classification | Interpretation | Number of Patients Affected
| High | 2 | 3 | 3 | 4 | 5
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Severity | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
| Likelihood Category | Interpretation | [5 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
| Very high | Certain or almost certain; highly likely to occur | [5 empty] | Severe psychological trauma | Multiple
| High | Not certain but very possible; reasonably expected to occur in the majority of cases |  |  |  |  | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
| Medium | Possible | [5 empty] | Severe psychological trauma | Single
| Low | Could occur but in the great majority of occasions will not | [5 empty] | Minor injury or injuries from which recovery is not expected in the short term | Multiple
| Very low | Negligible or nearly negligible possibility of occurring | [5 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
[8 empty] | Significant psychological trauma | Single
| 5 | Unacceptable level of risk | [5 empty] | Minor injury from which recovery is expected in the short term | Multiple
| 4 | Mandatory elimination of hazard or addition of control measure to reduce risk to an acceptable level | [5 empty] | Minor psychological upset; inconvenience | Multiple
| 3 | Undesirable level of risk. Attempts should be made to eliminate the hazard or implement control measures to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical |  |  |  |  | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible consequence | Single
| 2 | Acceptable where cost of further reduction outweighs benefits gained or where further risk reduction is impractical
| 1 | Acceptable, no further action required

## References
Reference | Description | Version | Doc. No.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16