## Cover Page
FHIR Mapping
| Programme | Operations and Assurance Services | Document Record ID Key
| Sub-Prog / Project | Clinical Safety
| Prog. Director | Dr Manpreet Pujara | Status | Final
| Owner | Stuart Harrison | Version | 1
| Author | Zak Bickhan / Sandy Garrity | Version Date | 2018-04-23
Generic Hazard Log
Document Purpose
This is a generic hazard log that details generic hazards for NHS Digital programme releases. It should be used by safety engineers and clinical safety officers in providing generic hazards to suppliers.
Copyright © 2018 Health and Social Care Information Centre.
NHS Digital is the trading name of the Health and Social Care Information Centre.

## Version History
Amendment History
Version | Date | Amendment History
0.1 | 2017-11-10 | Initial FHIR Interoperability Mapping Generic Hazard Review
0.2 | 2018-03-12 | Completion FHIR Interoperability Mapping ToC/GP Connect Generic Hazard Review
0.8 | 2018-04-19 | FHIR Interoperability Mapping ToC/GP Connect Generic Hazard Review Workshop
1 | 2013-04-23 | FHIR Interoperability Mapping ToC/GP Connect Generic Hazard Review
Reviewers
This document must be reviewed by the following:
Name |  | Title / Responsibility | Date | Version
Zak Bickhan |  | Clinical Safety Officer | 2018-04-23 | 1
Sandy Garrity |  | Safety Engineer | 2018-04-23 | 1
Amir Mehrkar |  | Senior Clinical Lead, Interoperability & Architecture | 2018-04-23 | 1
Approved
This document must be approved by the following:
Name |  | Title / Responsibility | Date | Version
Zak Bickhan |  | Clinical Safety Officer | 2018-04-23 | 1
Sebastian Alexander |  | Strategic Clinical Lead for Patient Safety | 2018-04-23 | 1
Stuart Harrison |  | Head of Safety Engineering | 2018-04-23 | 1
Distribution
NHS Digital Clinical Safety Personnel
Document Status:
The controlled copy of this document is maintained in NHS Digital corporate network. Any copies of this document held outside of that area, in whatever format (e.g. paper, email attachment), are considered to have passed out of control and should be checked for currency and validity.

## Hazard log
FHIR Mapping Generic Hazards | [5 empty] | Initial Risk Rating |  |  | Additional Controls |  |  |  | Residual Hazard Risk Rating
Hazard No | Hazard Name | Hazard Description | Potential Clinical Impact | Possible Causes | Existing Controls | Likelihood | Consequence | Risk | Design | Test | Training | Business Process Change | Likelihood | Consequence | Risk | Summary of Actions | Owner | Status
FHIR001 | Lack of alignment with other standards | The standards may not be consistent with the latest version of related standards e.g. Emergency Care Data Set, SNOMED CT subsets / terminology standards, PRSB standards, etc. | Health/care records used in different sites across various clinical and social settings would have a lack of interoperability / standardisation in their records. This could lead to inappropriate care or delay in the delivery of care. | Lack of support for an agreed standard. As existing standards are updated they may be misaligned to the headings. | Use of any existing standards. | Medium | Considerable | 3 | Maintenance of the standards is the responsibility of NHS Digital and changes must be possible for integration with relevant data standards as they change. Ensuring alignment with other relevant clinical standards. Consider new versioning/release (data standards team) |  |  | Consider new versioning/release (data standards team) - Munish to follow up with Dave Barnett | Low | Considerable | 3
FHIR002 | Mapping of PRSB information models to the FHIR target is not correct | Specification may not match existing standards or record structures e.g. PRSB standards, | This may lead to important clinical information being sent or received under wrong context which ccause delay to the assessment/treatment of the patient, and potentially inappropriate care. | Errors in intial mappings , erros in implmenting changes in FHIR CareConnect Profiles. | The mappings are reviewed by core team and later on by INTEROPen curation calls attendees. | Medium | Significant | 2 | Guidance notes to be provided in making meaning of section headings and content as understandable as possible. Section headings to be devised as a result of collaborative work with suppliers, with gap analysis as to differences between them, and identification of where PRSB do not have the equivalent. |  | Local organisation and end-user training to ensure understanding of the supplementary nature of the information presented |  | Low | Significant | 2
FHIR003 | Human readable narrative text might not match the structured or unstructured data in transfer of care documents | Data could be sent as coded data rather than text. If coded information is carried without associated text it may not be comprehensible in the Transfer of Care discharge summaries. | Patients may receive incorrect diagnosis or treatment. | Sending system or receving systems transform of FHIR message is not correct. | The FHIR standards implmentation assumes that narrative text should match the structured and unstructured data. | Medium | Considerable | 3 | Include associated text with any coded field. SNOMED CT is the only coded data that can be carried in outpatient letter communications (eg not READ, OPCS, etc) | This is tested in solution assurance by development of a renderer and messages are clinically assured. This is tested at each implmementation site before going live. | Implementers to provide guidance on any issue/risk might arise in use or misuse of their products. |  | Low | Considerable | 2
FHIR004 | Data Content Inconsistency Also refer to FHIR005 | Interpretation of the specification by 3rd parties may vary, leading to differences between specification intention and implementation. Specification may not match content of source system. (system not bolt that way) This hazard is concerned with multiple data sources all providing the same or similar data elements in varying formats. e.g. not compliant with mandatory value set descriptors, and inconsistencies with headings descriprtions in documents. | Multiple variations in data content or an inconsistent use of terms may lead to difficulties in the interpretation of the record. Use of non standard terms, local abbreviations or codes that are unfamiliar to systems using these data items, and users interacting with those systems may result in delayed or inappropriate care. | Lack of standardisation of the [html] structure and content of data across systems' suppliers. No guidance on the definition, use or localisation of data items provided to those systems between the provider and the receiver in rendering the html/xml messages. | Implmentation guidance is issued with the FHIR specifications. | Medium | Major | 3 | Specification and supplier engagement aims for standardisation as far as possible, but where this is not possible: - guidance notes provided as part of the specification, making clear of any supplier differences - requirement for relevant informative message to be supplied | Specification must be tested as part of clinical assurance and validation. Solution assurance and FOT testing to be completed. | Local organisation and end-user training to ensure understanding that the purpose of FHIR mapping is to supplement the information available to support patient direct care, not replace any other information sources. |  | Very Low | Major | 2
FHIR005 | Unclear headings Also refer to FHIR004 | Inconsistent use of (too many, unclear) headings which might not be supported by some systems. | Inconsistencies in clinical data transfer between systems. Incorrect data transfer - data are presented under an inappropriate heading, resulting in being missed or misinterpreted by the clinicians. Critical clinical information may be omitted which can cause an adverse effect on patient safety. Incorrect information entered under an inappropriate heading, leading to inappropriate treatment. | Incorrect data entry as it is unclear what heading information should be recorded against, due to poor understanding of headings. The headings are grouped in a way that might not work for a speciality/service/clinician. Too many headings will be time consuming and burdensome which may result in omission of key clinical information. The names and definitions of headings do not match between different systems. Clinicians unable to add information because the headings are not in their systems. | Use of current headings available in current local or national system such as SCRa. | Medium | Major | 3 | Systems' implementers to consider heading and field definitions to capture critical data. Implementers have to ensure they have the most up to date version of the headings, and that the headings are correctly implemented in their systems. Clear definitions of the information content under each heading, avoiding overlap. | Appropriate testings to ensure that the system can support all defined headings. | Training materials to consider users to be trained to use headings appropriately, and to complete only fields that are relevant to individual patient/specialty. | IT systems will be required to support all the headings, however, not all headings will be mandatory for implementers. Local agreements should determine the optional headings to be used by a particular system which must match those in the record standard. | Very Low | Major | 2
FHIR006 | Receiving systems automatically processes medication information | Prescription is incorrect and not as the Prescriber intended. | Incorrect medication dispensed to patient which can lead to severe consequences to patient health. | Incorrect mapping. System design prescriber preference. A dose based medication item from secondary care may be converted to the wrong product based medication item in primary care either as a result of human transcription error or as a result of automated/semi-automated conversion. | Pharmacists may act as a control but may not be able to translate the text into meaningful data and recover the problem. | Low | Major | 3 | Human readable rendition of original dose based prescription preserved and presented to primary care prescriber to facilitate cross check. | Clinical validation assurance testing to cover all prescribing formats. | Relevant training materials to be produced/updated by suppliers of secondary and primary care to cover the various prescribing formats. | All clinicians should review medication message content before accepting into their systems. | Very Low | Major | 2
FHIR007 | Ambiguity in negated (drug allergy) codes | FHIR allows negation in codeable concepts. It is posible to include negation statements that apply at the level of the whole list and it is also possible to have separate lists for thing like medication allergies. Adding new AllergyIntolerances to the list can cause confusion that any negation statements that are voided by the addition of a new record are/are not removed from the list. For e.g. if the list contains a "no known food allergies" record and a user/system add an "intolerance to grape flavour" record, then users/systems might/might not remove the "no known food allergies" record [must be sure this entry is removed]. | Incorrect medications may be given based on incomplete clinical information leading to potential delay in care. Incorrect medication dispensed to patient which can lead to severe consequences to patient health. | A variety of negated allergy codes options that are available which clinicians can choose. | Users/systems may differentiate between affirmatively stating that a patient has no known allergies versus either not including allergies in the record; or asserting that allergies were not reviewed and are unknown. | Medium | Considerable | Major | Prior to adding new allergy/intolerance, a list of existing negated and refuted [rules out with the high level of clinical certainty] reactions should be reviewed and reconciled. Negated codes [if stripped out] must not be sent if there are positive codes. Send everything except negative codes. Text should reflect actual meaning of the [allergy] codes - representing the real meaning of the code. The sending party to ensure that communication is well formed. | Clinical validation assurance testing to cover negated codes. | Relevant training materials to be produced/updated by suppliers of secondary and primary care to cover the various available negated codes. |  | Low | Considerable | 2
FHIR008 | M&A (Linked to risk id FHIR13 - Transcription error) | Inconsitencies on the way Coded/Uncoded/Local Coded Allergies are recorded | The way Allergies are currently coded in GP Clinical Systems is not standard. Different suppliers use different coding systems some of which are propietary to that particular system (EMIS). There is a SNOMED subset for allergy causative agents that has been published by TRUD but none of the GP systems currently use it. | It will be not be possible for consuming systems to safely trigger comprehensivily decision support systems from the allergy codes that GP suppliers currently use and it applies to secondary care to primary care. This could result in a patient being prescribed/administered incorrect medication which could cause deleterious effects, trigger an allergy or worsen a clinical condition. | 1.Consuming systems not being able to understand multiple coding systems some of which are proprietary. To note that there is national work to ensure that this situation is resolved and that Gp providers can implement a set of allergy codes that are commonly udnerstood. This hazard will be revisited | High | Major | Considerable | GP Connect Specification to include the complete record of patient allergies and adverse reactions, including allergies to drugs, foods and substances, and drug interactions. Specification clearly states the limitation that allergy codes can not be used for decisions support until this is resolved. Work is on going to write implementation guidance for GP suppliers. |  |  | The receving system clinicians will review all allergy headings content (Professional requirement) and then enter approprite allergy information manually. In GP2GP prescribing module is inactivated until inbound allergy content has been reviewed by the clinician. We recommend alignment to same principle as GP2GP in CareConnect FHIR implementations | Low | Considerable | 2
FHIR009 | Lack of standard presentation layer | There are a number of differences to the way that each application displays the data which could result in user confusion. For example, current beta version for Medication Section headings and content structure is not as 'clear' as it could be. | Clinical information may be presented in an unfamiliar order, or in an unexpected format. This may lead to important clinical information being missed, leading to a delay to the assessment/treatment of the patient, and potentially inappropriate care. | There are no national standards on the presenation layer . | Implementation guidance is issued re presentation of key clinical information e.g. medications. | Medium | Significant | 2 | Include presentation guidance when available from national sources e.g. National patient safety agency | This is tested as part of test harness for the transfer of care and example renderer to show example presentation. |  |  | Low | Significant | 2
FHIR010 | Transcription error | Receiving systems is unable to process the SNOMED CT code and degrades this to text | wrong medication or clinical information is entered manually (in error) in the clinical system by user | The receieving system is only able to process a subset of SNOMED CT codes | Implementation guidance to deprecate to text | Medium | Considerable | 3 | Implementation guidance to be issued with the FHIR release identifying this possible receiving system risk and alerts for users. |  | Exisiting end user local training to use system |  | Low | Considerable | 2
12 16 dmd 11 1 24/scr001 2/3/4/5/20 6 17
GP connect meds and allergies structured

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Consequence Category | Interpretation
| High | 2 | 3 | 3 | 4 | 5 |  | Consequence | Patients Affected
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Consequence | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
[8 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
[8 empty] | Severe psychological trauma | Multiple
[7 empty] | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
[8 empty] | Severe psychological trauma | Single
[8 empty] | Minor injury or injuries from which recovery is not expected in the short term. | Multiple
[8 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
[8 empty] | Significant psychological trauma | Single
[8 empty] | Minor injury from which recovery is expected in the short term | Multiple
[8 empty] | Minor psychological upset; inconvenience | Multiple
[7 empty] | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible consequence | Single
[7 empty] | Likelihood Category | Interpretation
[7 empty] | Very high | Certain or almost certain; highly likely to occur
[7 empty] | High | Not certain but very possible; reasonably expected to occur in the majority of cases
[7 empty] | Medium | Possible
[7 empty] | Low | Could occur but in the great majority of occasions will not
[7 empty] | Very low | Negligible or nearly negligible possibility of occurring